## Phase-Wise Development Roadmap

This roadmap breaks development into 4 phases for a lean, iterative build. Each phase delivers a testable increment with core value. Total estimated timeline assumes a 4–6 developer team: ~3 months to MVP (end of Phase 2), full Phase 4 in ~6–8 months.

Assumptions:

- Tech stack: Backend (Node.js/Python), Frontend (React), Database (PostgreSQL), GitHub API integration.

- Agile sprints: 2 weeks each.

- Each phase includes: Core features, basic testing, deployment to staging/production.

- Cross-cutting: Authentication (JWT), notifications (email + in-app), responsive UI, basic analytics dashboard for admins.

## Phase 1: Foundation & Core User Management (Sprint 1–3, ~6 weeks)

Goal: Get users onboarded and basic platform operational. No project applications yet.

Key Deliverables:

- User registration/login:

  - Intern: Self-register, email verification, profile/resume upload (1 resume max).

  - Guide: Admin-only creation, first-time password reset, profile setup.

  - Admin: Secure login.

- Basic dashboards:

  - Intern: My profile, completed internships (stub).

  - Guide: My profile, projects list (empty).

  - Admin: Guides list, projects overview (empty).

- Project creation (guide-only):

  - Draft mode: Title, description, scope, use cases, phases, duration, roles/skills.

  - Save as draft only—no publishing.

- Infrastructure:

  - Database schema (users, profiles, resumes, projects).

  - File storage for resumes (S3/AWS).

  - Basic API endpoints.

Success Criteria:

- 10 test interns can register and upload resumes.

- 5 test guides can create draft projects.

- Admin can create/manage 5 guides.

Out of Scope: Project publishing, applications, matching.

## Phase 2: MVP Core – Projects & Applications (Sprint 4–7, ~8 weeks)

Goal: Enable full intern–project matching flow and basic team formation. This is your functional MVP.

Key Deliverables:

- Project lifecycle (guide):

  - Publish project (sets application window).

  - View applicants per role (list with profile preview, resume download).

- Intern features:

  - Browse/publish projects, view details.

  - Apply to projects/roles (within window).

  - View "My Applications" (status: Applied / Shortlisted / Rejected).

- Light matching (system + guide):

  - System auto-shortlists top 5–10 candidates per role by skill fitment score.

  - Guide reviews shortlist, marks "Selected" (system sends in-app/email notification to intern).

  - Intern accepts/rejects offer → assigned to project (one-project rule enforced).

- Team view:

  - Guide sees project team, GitHub repo link (manual entry for now).

  - Intern sees "My Project" dashboard.

- Opt-out:

  - Intern can opt-out → 1-month ban from new applications (tracked in profile).

- Admin oversight:

  - View all projects/applications.

  - Override assignments.

Success Criteria:

- End-to-end: Guide publishes project → interns apply → guide selects → intern accepts → team visible.

- 50 test applications processed; opt-out tested.

- Deploy to production.

Out of Scope: GitHub auto-integration, progress tracking, certificates.

## Phase 3: Execution & Completion (Sprint 8–11, ~8 weeks)

Goal: Support active projects through completion and certificates.

Key Deliverables:

- GitHub integration:

  - Auto-create private repo on first intern acceptance (under org account).

  - Add guide + interns as collaborators.

- Project progress (guide):

  - Update phase statuses (Not started/In progress/Completed) + comments.

  - Project status (On track/At risk).

- Project closure:

  - Guide marks "Ready for Review" + attaches demo/GitHub links.

- Admin review & certificates:

  - Admin approves project → auto-generate/downloadable PDF certificates for team.

- Enhanced notifications:

  - Email + in-app for offers, assignments, phase updates, approvals.

- Admin tools:

  - Audit logs for assignments/opt-outs.

  - Bulk guide management.

Success Criteria:

- 10 test projects fully completed with certificates issued.

- GitHub repos created successfully 100% of time.

- Admin approval flow tested end-to-end.

Out of Scope: Advanced analytics, messaging between users.

## Phase 4: Polish & Scale (Sprint 12–16, ~10 weeks)

Goal: Improve UX, reliability, and scalability for real user growth.

Key Deliverables:

- UX enhancements:

  - Project search/filter (by skills, duration, guide).

  - Resume parsing (extract skills/education for better matching).

  - Multiple resume support for interns.

- Advanced matching:

  - Configurable shortlist size, improved scoring (e.g., weighted skills).

- Reliability:

  - Error handling, retries for GitHub API.

  - Backup/restore, monitoring (Sentry/New Relic).

- Analytics dashboard (admin):

  - Metrics: Active projects, intern assignment rate, completion rate.

- Mobile responsiveness polish.

- Security audit + compliance (GDPR basics for resumes).

Success Criteria:

- Platform handles 1,000 concurrent users.

- User satisfaction surveys (internal beta).

- Production-ready for public launch.

Out of Scope for All Phases: Ratings, time tracking, attendance, payments, in-app chat, video interviews.